## Table of Contents
Backend: | Frontend:
Server | Google API Interface
Google API Logic | User Management
Database | Design/Interface

## Server
BACK | To Do | In Progress | Ran into Problems | To be Tested | Tested & Complete
Issues:
Build Server with Node Catapult |  |  |  |  | Complete URL paths are a concatenation of the pathname extensions from the middleware file and the routes file
Add support for Heroku |  | server written to support heroku deployment
Deploy on Heroku

## G API Logic
BACK | To Do | In Progress | Ran into Problems | To be Tested | Tested & Complete
Factors:
Driver Coordinates (Start & End)
Rider Coordinates (Start & End)
Issues:
Logic for comparing rider's coordinates to Driver's coordinates & Path
Logic for verifying similar directions
Optimization:
Reduce amount of waypoint to pathpoint comparisons
Store path information in db
Check for valid route to driver's path from user's start and end points
Generate multiple path options
Generate waypoints for rider pickup and drop off after Driver and rider are linked

## Database
BACK | To Do | In Progress | Ran into Problems | To be Tested | Tested & Complete
Issues: | Reminders: *every object POSTed to /api/profile or /api/createtrip/setroute must specify the user's driver status or it will default to false; |  |  |  | FYI: run "mongod --dbpath ." from database directory to run local mongo server. Mongo server must be started before Mongo shell (command: "mongo").
Build out Mongo Server |  |  |  |  | Complete URL paths are a concatenation of the pathname extensions from the middleware file and the routes file

## G API InterF
BACK | To Do | In Progress | Ran into Problems | To be Tested | Tested & Complete
Issues:
Hide other user's location
Phase 2:
Show route with rider start and end points as waypoints

## User Management
BACK | To Do | In Progress | Ran into Problems | To be Tested | Tested & Complete
Issues:
Format and send user info to db

## Design_Interface
BACK | To Do | In Progress | Ran into Problems | To be Tested | Tested & Complete
Issues:
Profile Maker | Needs: name, rider/driver, home address, destination address
Messaging | message capability between users | notifications for messages
Login/signup | Signup | Login
Search
authentication
Phase 2:
Time of departure
Radius of availability
Oauth